## 30-60-90 Execution Plan
Mal Credit Decision Platform — 30/60/90 Day Execution Plan
Launch-Critical = must be live on Day 1 of product launch ¦ Post-Launch = important but does not block revenue
Day 1–30 — Launch-critical foundation: data flowing, decisions traceable
Area | Task | Owner | Priority | Effort | Depends On | Notes
Infrastructure | Provision RDS PostgreSQL (Multi-AZ, me-south-1) | Infra | Launch-Critical | 2d | — | Aurora Serverless v2 target; RDS to start
Infrastructure | Create S3 bronze bucket — KMS-SSE, versioning ON | Infra | Launch-Critical | 1d | — | Bucket policy: DenyUnencryptedObjectUploads
Infrastructure | Set up MWAA (managed Airflow 2.9) | Infra | Launch-Critical | 2d | — | One worker node sufficient for 10K/day
Infrastructure | Secrets Manager entries: AECB key, fraud API key, webhook secret, DB DSN | Infra | Launch-Critical | 1d | RDS | No credentials in code or env vars
Database | Apply bronze schema DDL (4 tables) | DE | Launch-Critical | 1d | RDS | sql/bronze/create_bronze_tables.sql
Database | Apply silver schema DDL (5 tables + pg_trgm extension) | DE | Launch-Critical | 1d | Bronze DDL | sql/silver/create_silver_tables.sql
Database | Apply gold schema DDL (decision snapshots + DQ scorecard) | DE | Launch-Critical | 1d | Silver DDL | sql/gold/*.sql + sql/data_quality/dq_rules.sql
Ingestion | Deploy AECB SFTP ingester — test with sample XML files | DE | Launch-Critical | 3d | Bronze DDL | Coordinate SFTP credentials with AECB; validate Emirates ID parsing
Ingestion | Deploy Fraud API ingester — integrate with application flow | DE | Launch-Critical | 2d | Bronze DDL | Confirm API key, rate limits, and SLA with provider
Ingestion | Deploy AML webhook receiver behind API Gateway | DE | Launch-Critical | 2d | Bronze DDL | Set idempotency; validate webhook secret rotation plan
Ingestion | Deploy customer profile CDC extractor — full load first | DE | Launch-Critical | 2d | Bronze DDL | Confirm updated_at index exists on source PostgreSQL
Identity Resolution | Run silver/identity_resolution.sql — validate against test data | DE | Launch-Critical | 2d | All ingestion | Test cross-source matching with real Emirates IDs
Identity Resolution | Tune pg_trgm threshold on Arabic names (sample 500 records) | DE | Launch-Critical | 2d | Identity resolution | Arabic transliterations require lower threshold — document exceptions
Decisioning | Wire gold.create_decision_snapshot() into application API | DE+Eng | Launch-Critical | 3d | Silver tables | Every credit decision must call this function before returning a result
Data Quality | Activate DQ scorecard engine — MUST_PASS rules only | DE | Launch-Critical | 2d | Gold DDL | Connect SNS → team Slack for MUST_PASS failures
Orchestration | Deploy Airflow DAG — run end-to-end with real data | DE | Launch-Critical | 2d | All above | Validate short-circuit gate on DQ failures
Compliance | Verify audit chain: gold FK → silver FK → bronze raw payload | DE+Legal | Launch-Critical | 1d | Gold DDL | Write a sample audit query; review with compliance officer
Testing | Load test at 10K decisions/day sustained for 4 hours | DE+QA | Launch-Critical | 2d | Full pipeline | Measure p95 latency on snapshot insert; index if > 200ms
Day 31–60 — Stabilise, monitor, and harden for growth to 30K/day
Area | Task | Owner | Priority | Effort | Depends On | Notes
Data Quality | Activate HIGH and MEDIUM DQ rules | DE | Post-Launch | 2d | Day 30 DQ | Set alert thresholds based on first 30 days of actual data
Data Quality | Build gold.v_dq_alerts dashboard in CloudWatch or Metabase | DE | Post-Launch | 2d | DQ rules live | Risk team needs daily DQ health view
Portfolio Monitoring | Activate portfolio_daily_snapshot refresh (daily CALL) | DE | Post-Launch | 1d | Day 30 pipeline | Schedule as separate Airflow task after gold refresh
Portfolio Monitoring | Build approval rate trend dashboard (v_approval_rate_trend) | Analytics | Post-Launch | 3d | Snapshot live | Connect Metabase or QuickSight to gold schema read replica
Portfolio Monitoring | Build risk concentration matrix (v_risk_concentration) | Analytics | Post-Launch | 2d | Snapshot live | Cross-tab: score band × DTI band — CRO weekly review
Identity Resolution | Review identity_resolution_exceptions backlog weekly | DE | Post-Launch | Ongoing | Day 30 pipeline | Set up weekly Airflow task to email count + sample
Reliability | Add dead-letter queue for failed AML webhook deliveries | DE+Infra | Post-Launch | 2d | Webhook live | Provider retries 3×; DLQ catches remainder for manual reprocess
Reliability | Implement Airflow SLA missed alerts (DAG must complete by 06:00) | DE | Post-Launch | 1d | Airflow DAG | Pipeline must complete before business opens at 09:00 UAE
Reliability | Add RDS CloudWatch alarms: CPU > 70%, free storage < 20 GB | Infra | Post-Launch | 1d | RDS live | Auto-scaling storage enabled; alarm before it's needed
Security | Column-level encryption for Emirates ID and DOB in silver/gold | DE+Sec | Post-Launch | 4d | Silver DDL | Use pgcrypto or AWS RDS encryption + application-layer masking
Security | Implement row-level security: analysts can only see their product | DE+Sec | Post-Launch | 2d | Silver DDL | RLS policies on gold.credit_decision_inputs by product_type
Performance | Add partial indexes on gold for common filter patterns | DE | Post-Launch | 1d | 30d of data | e.g. WHERE decision_outcome = 'APPROVED' AND decided_at > NOW()-30d
Performance | Profile identity resolution queries; add GIN index on full_name if needed | DE | Post-Launch | 2d | 30d of data | pg_trgm GIN index accelerates similarity() lookups 10–50×
Documentation | Write data dictionary for all silver and gold tables | DE | Post-Launch | 3d | Schema stable | Required for CBUAE audit; include data lineage notes
Process | Weekly DQ review cadence with risk team (30-min meeting) | DE+Risk | Post-Launch | Ongoing | DQ live | Review dq_scorecard trends; adjust thresholds as needed
Day 61–90 — Scale to 100K/day, analytics layer, and CBUAE readiness
Area | Task | Owner | Priority | Effort | Depends On | Notes
Scale | Migrate gold analytics queries to S3 Parquet + Athena | DE+Infra | Post-Launch | 5d | Day 60 stable | 30K+/day makes RDS analytics queries expensive; Athena = pay-per-scan
Scale | Automate Parquet export: gold tables → S3 daily via Airflow | DE | Post-Launch | 3d | Athena ready | Partition by product_type/snapshot_date for efficient pruning
Scale | Upgrade RDS to Aurora Serverless v2 (auto-scales to 100K/day) | Infra | Post-Launch | 3d | Load test | Blue/green deployment; < 1 min failover; no downtime
Scale | Load test at 100K decisions/day (simulate with Locust) | DE+QA | Post-Launch | 3d | Aurora upgrade | Acceptance: p95 snapshot insert < 500ms, DQ run < 10 min
Analytics | Build CBUAE regulatory report (auto-generated from gold) | DE+Compliance | Post-Launch | 5d | Gold stable | Monthly report: approvals by nationality, product, DTI band
Analytics | Set up Redshift Serverless for cross-product analytics (optional) | Infra | Post-Launch | 4d | Parquet on S3 | If Athena query latency > 10s on complex joins; evaluate vs cost
Fraud | Build velocity monitoring: >3 applications/customer/7 days alert | DE+Fraud | Post-Launch | 3d | Gold 30d data | Fraud rings often submit multiple applications with slight variations
Fraud | Integrate fraud score trend: flag rising scores on existing customers | DE | Post-Launch | 2d | 60d fraud data | Silver fraud_scores.customer_key allows longitudinal view
ML Readiness | Export feature store snapshot from silver for model training | DE+DS | Post-Launch | 4d | Silver stable | Train initial scorecard model on first 60 days of decisions
ML Readiness | Add model_version column to gold.credit_decision_inputs | DE | Post-Launch | 1d | Gold stable | Needed to A/B test scorecard models in production
Compliance | Full CBUAE audit trail dry-run: trace 50 random decisions end-to-end | DE+Legal | Post-Launch | 2d | All layers | Document findings; resolve any gaps before formal audit
Compliance | Implement data access log (who queried what PII, when) | Infra+DE | Post-Launch | 3d | RLS live | CloudTrail + RDS audit log → CloudWatch; 1-year retention
Reliability | Implement cross-region S3 replication for bronze bucket | Infra | Post-Launch | 1d | S3 stable | DR requirement: RPO < 24h; RTO < 4h for bronze data
Process | Runbook for common failure modes (stale AECB, webhook gap) | DE | Post-Launch | 3d | 60d operations | On-call engineers need step-by-step remediation guides

## Success Metrics
Success Criteria by Phase
Day 30 Success Criteria
✓ Metric | All 4 bronze sources ingesting daily without manual intervention
✓ Metric | 100% of credit decisions have an entry in gold.credit_decision_inputs
✓ Metric | DQ MUST_PASS rules: 0 failures in 7 consecutive days
✓ Metric | Audit chain query returns complete lineage for 100% of approved decisions
✓ Metric | Pipeline completes by 06:00 UAE time for 10K decisions/day
Day 60 Success Criteria
✓ Metric | DQ HIGH rules: pass rate ≥ threshold for 95% of daily runs
✓ Metric | Portfolio dashboard live and reviewed by risk team weekly
✓ Metric | Identity resolution exception rate < 2% of daily applications
✓ Metric | Zero PII data accessible without RLS enforcement
✓ Metric | Incident response: DQ alert to resolution < 2 hours (P1)
Day 90 Success Criteria
✓ Metric | Pipeline handles 100K decisions/day: p95 snapshot insert < 500ms
✓ Metric | CBUAE audit dry-run: 100% of sampled decisions fully traceable
✓ Metric | Athena analytics query latency < 10s on 90-day lookback
✓ Metric | Monthly CBUAE regulatory report auto-generated with 0 manual edits
✓ Metric | Feature store available for model training on full 90-day dataset

## RACI
RACI — Responsibility Matrix
Workstream | Data Engineering | Infra/DevOps | Analytics | Risk/Compliance | Engineering
Bronze ingestion (all 4 sources) | R/A | C | I | I | C
Identity resolution logic | R/A | I | C | C | I
Gold decision snapshot function | R/A | I | I | I | C
Data quality rules & thresholds | R | I | I | A | I
Portfolio monitoring mart | R | I | A | C | I
AWS infrastructure provisioning | C | R/A | I | I | I
Airflow DAG orchestration | R/A | C | I | I | I
CBUAE compliance audit trail | C | I | I | R/A | I
Fraud API & AML provider integration | R | C | I | A | C
Analytics dashboards | C | I | R/A | C | I
Security & PII encryption | C | R | I | A | C
Load testing & performance | R | C | I | I | A
R = Responsible · A = Accountable · C = Consulted · I = Informed